## Tasks
Task ID | Task Name | Parent ID | Parent Name | Status | Due Date | Time Estimate (h) | Tags | Costs PM | Costs PO | Costs BA | Costs RM | Costs SA | Costs DEV | Costs TAN | Costs TAR | Costs TM | Costs Total
86c20vezb | 1. Project Planning |  |  | OPEN | 2025-03-14 | 80 | business analyst, product owner, project manager, requirements manager | 6000 | 4000 | 3500 | 4500 | 0 | 0 | 0 | 0 | 0 | 18000
86c20veze | 1.1. Define Requirements | 86c20vezb | 1. Project Planning | OPEN | 2025-03-07 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vezg | 1.2. Allocate Resources | 86c20vezb | 1. Project Planning | OPEN | 2025-03-14 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf0y | 2. UI-Rebranding |  |  | OPEN | 2025-03-28 | 80 | business analyst, project manager, solution architect | 6000 | 0 | 3500 | 0 | 5000 | 0 | 0 | 0 | 0 | 14500
86c20vf10 | 2.1. Designing New UI | 86c20vf0y | 2. UI-Rebranding | OPEN | 2025-03-21 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf13 | 2.2. Implement New UI | 86c20vf0y | 2. UI-Rebranding | OPEN | 2025-03-28 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf21 | 3. AD/DA Driver Development |  |  | OPEN | 2025-05-01 | 192 | project manager | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400
86c20vf26 | 3.1. Community Driver Development | 86c20vf21 | 3. AD/DA Driver Development | OPEN | 2025-04-21 | 128 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf28 | 3.2. Unit Testing | 86c20vf21 | 3. AD/DA Driver Development | OPEN | 2025-05-01 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf2z | 4. VST Licensing & Porting |  |  | OPEN | 2025-05-20 | 104 | developer, project manager, solution architect | 7800 | 0 | 0 | 0 | 6500 | 5200 | 0 | 0 | 0 | 19500
86c20vf30 | 4.1. License Shareware VSTs | 86c20vf2z | 4. VST Licensing & Porting | OPEN | 2025-05-08 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf35 | 4.2. Port VSTs to ARMband | 86c20vf2z | 4. VST Licensing & Porting | OPEN | 2025-05-20 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf2f | 5. Case Tooling & Manufacturing |  |  | OPEN | 2025-05-29 | 56 | project manager | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
86c20vf2g | 5.1. Tooling Design | 86c20vf2f | 5. Case Tooling & Manufacturing | OPEN | 2025-05-27 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf2j | 5.2. Mass Production | 86c20vf2f | 5. Case Tooling & Manufacturing | OPEN | 2025-05-29 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf3d | 6. Testing & QA |  |  | OPEN | 2025-06-20 | 128 | developer, project manager, test analyst, test architect, test manager | 9600 | 0 | 0 | 0 | 0 | 6400 | 6400 | 8000 | 7200 | 37600
86c20vf3g | 6.1. Integration Testing | 86c20vf3d | 6. Testing & QA | OPEN | 2025-06-05 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf3j | 6.2. Hardware Testing | 86c20vf3d | 6. Testing & QA | OPEN | 2025-06-10 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf3n | 6.3. User Acceptance Testing | 86c20vf3d | 6. Testing & QA | OPEN | 2025-06-17 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf3u | 6.4. Performance Testing | 86c20vf3d | 6. Testing & QA | OPEN | 2025-06-20 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c20vf70 | 7. Project Closure |  |  | OPEN | 2025-06-24 | 16 | business analyst, project manager | 1200 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 1900
[8 empty] | 49200 | 4000 | 7700 | 4500 | 11500 | 11600 | 6400 | 8000 | 7200

## Rates
Role | Daily Rate (£) | Responsibilities
Project Manager | 600 | Planning, resourcing, reporting.
Project Analyst | 250 | WBS code mgmt., costing, allocation.
Test Manager | 450 | Test planning, organising, reporting.
Test Architect | 500 | Test design, co-planning, scripting.
Test Analyst | 400 | Test execution, recording, reporting.
Solution Architect | 500 | Software/System Design, Integration.
Developer | 400 | Software coding and Implementation.
Product Owner | 400 | UAT, Stakeholder representation.
Requirements Manager | 450 | Requirements gathering and analysis.
Business Analyst | 350 | Requirements analysis, business design.