## Tasks
Task ID | Task Name | Parent ID | Parent Name | Status | Due Date | Time Estimate (h) | tags | Costs PM | Costs PO | Costs BA | Costs RM | Costs SA | Costs DEV | Costs TAN | Costs TAR | Costs TM | Costs Total
86c22yby0 | 1. Project Planning |  |  | OPEN | 2025-03-14 | 80 | business analyst, product owner, project manager, requirements manager | 6000 | 4000 | 3500 | 4500 | 0 | 0 | 0 | 0 | 0 | 18000
86c22yby4 | 1.1. Define Requirements | 86c22yby0 | 1. Project Planning | OPEN | 2025-03-07 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ybyc | 1.2. Allocate Resources | 86c22yby0 | 1. Project Planning | OPEN | 2025-03-14 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ybyu | 2. UI-Development |  |  | OPEN | 2025-04-07 | 128 | business analyst, project manager, solution architect | 9600 | 0 | 5600 | 0 | 8000 | 0 | 0 | 0 | 0 | 23200
86c22ybyz | 2.1. Designing Standardised UI | 86c22ybyu | 2. UI-Development | OPEN | 2025-03-26 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ybz3 | 2.2. Implement New UI | 86c22ybyu | 2. UI-Development | OPEN | 2025-04-07 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ybzn | 3. Driver and Software Porting |  |  | OPEN | 2025-05-30 | 320 | project manager | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
86c22ybzu | 3.1. Port Supercollider Engine | 86c22ybzn | 3. Driver and Software Porting | OPEN | 2025-04-16 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ybzx | 3.2. Port Lua Interpreter | 86c22ybzn | 3. Driver and Software Porting | OPEN | 2025-04-28 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ydfr | 3.3. Develop Sound Driver | 86c22ybzn | 3. Driver and Software Porting | OPEN | 2025-05-08 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22ydjm | 3.4. Unit Testing | 86c22ybzn | 3. Driver and Software Porting | OPEN | 2025-05-30 | 128 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc10 | 4. Case Design & 3D Printing |  |  | OPEN | 2025-06-16 | 88 | developer, project manager, solution architect | 6600 | 0 | 0 | 0 | 5500 | 4400 | 0 | 0 | 0 | 16500
86c22yc16 | 4.1. Design Case | 86c22yc10 | 4. Case Design & 3D Printing | OPEN | 2025-06-06 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc1d | 4.2. 3D Printing Prototypes | 86c22yc10 | 4. Case Design & 3D Printing | OPEN | 2025-06-11 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yfav | 4.3. 3D Printing Final Case | 86c22yc10 | 4. Case Design & 3D Printing | OPEN | 2025-06-16 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc06 | 5. Product Assembly |  |  | OPEN | 2025-07-08 | 128 | project manager | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600
86c22yc1m | 6. Testing & QA |  |  | OPEN | 2025-08-28 | 296 | developer, project manager, test analyst, test architect, test manager | 22200 | 0 | 0 | 0 | 0 | 14800 | 14800 | 18500 | 16650 | 86950
86c22yc23 | 6.1. Community Integration Testing | 86c22yc1m | 6. Testing & QA | OPEN | 2025-07-30 | 128 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc27 | 6.2. Hardware Testing | 86c22yc1m | 6. Testing & QA | OPEN | 2025-08-11 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc29 | 6.3. User Acceptance Testing | 86c22yc1m | 6. Testing & QA | OPEN | 2025-08-21 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc2f | 6.4. Performance Testing | 86c22yc1m | 6. Testing & QA | OPEN | 2025-08-28 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86c22yc3x | 7. Project Closure |  |  | OPEN | 2025-09-02 | 16 | business analyst, project manager | 1200 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 78000 | 4000 | 9100 | 4500 | 13500 | 19200 | 14800 | 18500 | 16650

## Rates
Role | Daily Rate (£) | Responsibilities
Project Manager | 600 | Planning, resourcing, reporting.
Project Analyst | 250 | WBS code mgmt., costing, allocation.
Test Manager | 450 | Test planning, organising, reporting.
Test Architect | 500 | Test design, co-planning, scripting.
Test Analyst | 400 | Test execution, recording, reporting.
Solution Architect | 500 | Software/System Design, Integration.
Developer | 400 | Software coding and Implementation.
Product Owner | 400 | UAT, Stakeholder representation.
Requirements Manager | 450 | Requirements gathering and analysis.
Business Analyst | 350 | Requirements analysis, business design.